## Sheet1
S.No | Jira No | Review ID | Reviewer Name | Aproval Status | Submitted Date | Priority | Reject Reason | How Many times Resubmitted | Remarks/Comments
1 | ANG-6364 | 14462;14479 | James Perry | Needs Work | 2020-07-04 |  | Add blank line after method | 2
Remove ", which is recently added" from summary as it doesn't make sense.
Change data type on stackLayout to string.
Pluralize recentCarePlan as it's a List
Fix casing on method name, plan s/b Plan
CarePlan in summary s/b two words.
Fix casing - careplan s/b carePlan
2 | ANG-6369 | 14546 | James Perry | Finished with Comments | 2020-08-04 | Low | why was this submitted? All that was done was moving a line of code. | 1 | Commented with request id 14546, but not got any response yet.
3 | ANG-4613 | 14903;14934;14940;14956 | James Perry | Needs Work | 2020-04-22 |  | remove extra inserted spaces | 4
| ANG-6560 |  |  |  | 2020-04-23 |  | There was one space after ""
some blank space after success function call and want to know why i remove ":",
i replied as per BRD we don't want that ":"
4 | ANG-5013, ANG-5516 | 14937, 14947, 14995, 15003 | James Perry | Needs Work | 2020-04-24 | Low | Remove TODO | 4
add space
Remove line/space
rename, maybe requestTypeCodeDefs
remove Create (from existing variable)
Fix casing to match parameters
s/b ID
Casing like (s/b ID)
5 | ANG-55166 | "15036", "15043", "15046" | James Perry | Needs Work | 2020-04-27 | Midium | Casing in Comment Section(Low)
Remove Spaces(Low)
Aggree with StackLayout scenario
naming of css class
6 | ANG-4221 | "15089", | James Perry | Needs Work | 2020-04-28 | Low | s/b Enagement ,Space
|  | "15105" | James Perry | Waiting for review | 2020-04-29
7 | ANG-5220 | "15240" | James Perry | Needs Work | 2020-05-04 | Low | fix format
fix casing
top 10 is asked made T caps which is not caps in BRD
Majority issues are Plural collection names and space issues
All the issues fixed and sent for code review
|  | "15257" | James Perry | Needs Work | 2020-05-04 | Major | spaces and remove commented codes | 2 | Commented with request id 15257 (Need work) ,(15268 looks good)
8 | ANG-5612 | "15394" | James Perry | Needs Work | 2020-07-05 | High | spaces and remove commented codes | 2 | Commented with request id 15394 (Need work)
9 | ANG-7120 | "15470" | James Perry | Needs Work | 18/5/2020 | Major | Remove line/space | 2 | Commented with request Id 15593(Need work),(15603 looks good)